## Gantt Chart
Task | Task Type | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20
|  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1. Create survey to collect extra data from students | Research | bar: Week 9 M
2. Analyze original template structure | Research | bar: Week 9 T
3. Explore p5.table | Research | bar: Week 9 W
4. Study similar dashboards | Research | bar: Week 9 T
5. Apply MoSCoW method for feature prioritization | Research | bar: Week 9 F to Week 10 M
6. Define SWOT analysis for each proposed module | Research | bar: Week 9 F to Week 10 M
7. Identify limitations according to deadline | Research | bar: Week 10 T
8. Design flow diagram for app (interaction, logic and behavior) | Research | bar: Week 10 T
9. Create early drafts (paper) | Prototype | bar: Week 10 T
10. Plan user interaction and flow | Prototype | bar: Week 10 W
11. Test general ideas | Prototype | bar: Week 10 W
12. Choose fonts, colors and general spacing | Design | bar: Week 10 W
13. Organize components visually | Design | bar: Week 10 W
14. Create draft in Figma | Design | bar: Week 10 T
15. Add first extention mentioned in class | Development | bar: Week 10 F
16. Add second extention mentioned in class | Development | bar: Week 11 M
17. Create initial canvas background (CSS + HTML) | Development | bar: Week 11 T
18. Collect data from survey (2-week survey) | Development | bar: Week 11 T
19. Create a preliminary chart for the survey | Development | bar: Week 11 W to Week 11 T
20. Write report | Development | bar: Week 11 F
21. Tech Diversity Gender: Add legend + Add Mean for each gender | Development | bar: Week 13 M to Week 13 F
22. Tech Diversity Race: Duplicate charts and add buttons | Development | bar: Week 14 M to Week 14 F
23. Pay GAP(1997-2017): Add stacked bars and improve layout | Development | bar: Week 15 M to Week 16 T
24. AI Usage: Create bubble chart, add mean values, buttons and layout | Development | bar: Week 16 W to Week 18 F
25. Prepare final documentation | Development | bar: Week 19 M to Week 19 T
26. Test interactions | Testing | bar: Week 19 F to Week 20 M
27. Fix bugs and issues | Testing | bar: Week 20 T to Week 20 W
28. Create and collect survey for users feedback | Testing | bar: Week 20 T
To do
Done