## Gantt Chart
Task | Weight | Completion | Task Type | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20
|  |  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1. Create survey to collect extra data from students | 1% | 1% | Research | bar: Week 9 M
2. Analyze original template structure | 5% | 5% | Research | bar: Week 9 T
3. Explore p5.table | 2% | 2% | Research | bar: Week 9 W
4. Study similar dashboards | 2% | 2% | Research | bar: Week 9 T
5. Apply MoSCoW method for feature prioritization | 3% | 3% | Research | bar: Week 9 F to Week 10 M
6. Define SWOT analysis for each proposed module | 3% | 3% | Research | bar: Week 9 F to Week 10 M
7. Identify limitations according to deadline | 2% | 2% | Research | bar: Week 10 T
8. Design flow diagram for app (interaction, logic and behavior) | 3% | 3% | Research | bar: Week 10 T
9. Create early drafts (paper) | 2% | 2% | Prototype | bar: Week 10 T
10. Plan user interaction and flow | 2% | 2% | Prototype | bar: Week 10 W
11. Test general ideas | 2% | 2% | Prototype | bar: Week 10 W
12. Choose fonts, colors and general spacing | 1% | 1% | Design | bar: Week 10 W
13. Organize components visually | 1% | 1% | Design | bar: Week 10 W
14. Create draft in Figma | 3% | 3% | Design | bar: Week 10 T
15. Add first extention mentioned in class | 3% | 3% | Development | bar: Week 10 F
16. Add second extention mentioned in class | 3% | 3% | Development | bar: Week 11 M
17. Create initial canvas background | 3% | 3% | Development | bar: Week 11 T
18. Adjust charts according to new canvas | 7% | 7% | Development | bar: Week 10 T to Week 11 T
19. Create a preliminary chart for the survey | 2% | 2% | Development | bar: Week 11 W to Week 11 T
20. Write report | 6% | 6% | Development | bar: Week 11 F
21. Tech Diversity Gender: Add legend + Add Mean for each gender | 5% | 8% | Development | bar: Week 12 W to Week 13 M
22. Tech Diversity Race: Duplicate charts and add buttons | 5% | 0% | Development | bar: Week 13 F to Week 14 T
23. Pay GAP(1997-2017): Add stacked bars and improve layout | 5% | 5% | Development | bar: Week 14 F to Week 15 T
24. Pay GAP Per Job: Paint bubbles, add axis names and legend | 3% | 0% | Development | bar: Week 16 M to Week 16 T
25: Climate Change: Adjust slicers to fit into the canvas, adjust colors. | 3% | 0% | Development | bar: Week 17 M to Week 17 T
26. AI Usage: Create bubble chart, add mean values, buttons and layout | 12% | 9% | Development | bar: Week 17 W to Week 18 F
27. Prepare final documentation | 3% | 0% | Development | bar: Week 19 M to Week 19 T
28. Test interactions | 3% | 0% | Testing | bar: Week 19 F to Week 20 M
29. Fix bugs and issues | 3% | 0% | Testing | bar: Week 20 T to Week 20 W
30. Create and collect survey for users feedback | 2% | 0% | Testing | bar: Week 20 T
TOTAL COMPLETION | 100% | 78%
To do
Done